## Task Tracker
# | Phase / Deliverable | Task | Status | Owner | Due Date
1 | 1. Data Ingestion & Baselines | Select weather dataset & define target/outcome variable | Not Started
2 | 1. Data Ingestion & Baselines | Set up API access/keys (NOAA CDO API, api.weather.gov) | Not Started
3 | 1. Data Ingestion & Baselines | Establish evaluation metric aligned with forecasting constraints | Not Started
4 | 1. Data Ingestion & Baselines | Pull historical data and build raw dataset | Not Started
5 | 1. Data Ingestion & Baselines | Perform train/test split; isolate test set until production validation | Not Started
6 | 1. Data Ingestion & Baselines | Exploratory data analysis (EDA) on historical weather data | Not Started
7 | 1. Data Ingestion & Baselines | Establish baseline model performance | Not Started
8 | 2. Pipeline Automation & Experiment Tracking | Set up GitHub repository structure (branches, .gitignore) | Not Started
9 | 2. Pipeline Automation & Experiment Tracking | Build automated Airflow pipeline for preprocessing & training | Not Started
10 | 2. Pipeline Automation & Experiment Tracking | Implement feature store / data versioning | Not Started
11 | 2. Pipeline Automation & Experiment Tracking | Set up MLflow experiment tracking (params, metrics, artifacts) | Not Started
12 | 2. Pipeline Automation & Experiment Tracking | Evaluate AutoML for hyperparameter tuning / algorithm selection | Not Started
13 | 2. Pipeline Automation & Experiment Tracking | Run experiments and log results to MLflow | Not Started
14 | 2. Pipeline Automation & Experiment Tracking | Register finalized model to Model Registry with semantic versioning | Not Started
15 | 3. Containerization & Deployment | Build FastAPI inference service around registered model | Not Started
16 | 3. Containerization & Deployment | Containerize service with Docker | Not Started
17 | 3. Containerization & Deployment | Test API accepts inputs & returns real-time predictions | Not Started
18 | 3. Containerization & Deployment | Deploy for live/real-time data prediction | Not Started
19 | 4. Production Monitoring & Drift Simulation | Set up monitoring framework/dashboard (EvidentlyAI, Prometheus/Grafana) | Not Started
20 | 4. Production Monitoring & Drift Simulation | Baseline validation: run clean test set through API vs. monitoring baseline | Not Started
21 | 4. Production Monitoring & Drift Simulation | Build data/schema corruption script for drift simulation | Not Started
22 | 4. Production Monitoring & Drift Simulation | Send drifted data to deployed model (anomaly verification) | Not Started
23 | 4. Production Monitoring & Drift Simulation | Document & verify monitoring dashboard catches drift | Not Started
24 | 4. Production Monitoring & Drift Simulation | Set up automated model evaluation & alerting on new live data | Not Started
25 | Deliverable: GitHub Repository | Write fully commented source code | Not Started
26 | Deliverable: GitHub Repository | Write comprehensive README.md (setup + reproduction steps) | Not Started
27 | Deliverable: GitHub Repository | Add dependency file (requirements.txt / environment.yml / Dockerfile) | Not Started
28 | Deliverable: GitHub Repository | Clean up repo structure for professionalism | Not Started
29 | Deliverable: GitHub Repository | Publish repo publicly and confirm accessible link | Not Started
30 | Deliverable: Presentation (PPT) | Slide: Problem Statement & EDA overview | Not Started
31 | Deliverable: Presentation (PPT) | Slide: Evaluation Metric justification | Not Started
32 | Deliverable: Presentation (PPT) | Slide: System Architecture diagram | Not Started
33 | Deliverable: Presentation (PPT) | Slide: Experiment Tracking (MLflow dashboard) | Not Started
34 | Deliverable: Presentation (PPT) | Slide: Deployment & Monitoring (demo/screenshots) | Not Started
35 | Deliverable: Presentation (PPT) | Slide: Drift Analysis (visual evidence) | Not Started
36 | Deliverable: Presentation (PPT) | Slide: Repository link | Not Started
37 | Deliverable: Presentation (PPT) | Rehearse live demo / full run-through | Not Started | Whole Team